Patient Participation Group (PPG) meeting minutes

18th April 2023
Princes Risborough surgery

|  |  | Action |
| --- | --- | --- |
| 1. | Attendance / Apologies In attendance: LM-F - Lesley Munro-Faure, CJ – Charli Johnson, MM – Michael Mulholland (part) JH – Jackie Highe, JE - Jenny Edmans, MB - Matt Bateman, MM – Monica Marshall, CC – Cathy Clarke, MH – Miv Hughes, BJ – Brenda Jefford Apologies received: Rob Holdaway, Yvonne Hook, Pat Mullen, Marion Wilkes (stepping back from PPG for now) |  |
| 2. | Review of Minutes and Actions Minutes of meeting of 25.02.23 were approved. Actions were reviewed and all completed except the ones related to Klinik which are still outstanding and will be completed as part of the patient communications as we roll-out Klinik: - Plan how we will communicate Klinik change to patients - Dr M to write a paragraph informing patients why they should inform reception re their reason for needing an appt rather than saying ‘private’ - Dr M to arrange a video interview with RC to aid patient education re Klinik |  |
| 3. | Update on Klinik There are two parts to Klinik roll-out: Design the ‘front-end’ as it will appear for patients Design the ‘back end’, ie the internal structures, appointment books etc We have completed the ‘front end’ and Dr Mulholland attended to take the PPG through Klinik in detail and how it will look for patients so we can ensure this works for patients before we finalise the rest of the process and start to roll-out. The PPG were satisfied with the work that had been done and the need for a new on-line appointment system. Stressed that it won’t exclude those that can’t manage on-line – they will still be able to telephone/call in and reception will help them by completing the form with them. Nurse/HCA appointments won’t necessarily need to be booked this way (although we will enable on-line booking of some nurse appointments, which we have not done previously. Meeting then focused on the communication for patients: - Why needed – focus on helping patients get to the right person/right time - Don’t mention AI since this can be off-putting for patient - Would be useful if, once the form submitted, the patient receives confirmation of request received and what happens next (not sure of this and can’t test since ‘dummy’ system – will need to check with Klinik) - Communicate through TV screens, website, text, newsletter, video |  |
| 4. | Patient Survey The meeting then reviewed the patient survey in detail, discussing the responses to each question and then the action plan proposed by Unity Health. We have embedded the survey results and our initial analysis in the minutes here: We have also embedded the agreed action plan here: Final item we discussed was the newsletter and what we might do to raise its profile amongst patients. We recognise and appreciate the significant amount of work that goes into the newsletter and want to make sure we are able to make the most of this work. Last newsletter was Spring 2022 | Action: LM-F to implement agreed actions Action: JH to discuss with YH/MW |
| 5. | Staff Changes LM-F provided an update on staff changes - We have recruited two new GP Partners – Dr Rodger will start 1st June 2023 and Dr Dennis Phang will start as soon as his pre-employment checks are complete. We have also recruited a new salaried GP – plan to start August 2023 – further details to follow. |  |